## AI Requirement
AI Demo Project – Candidate Assignment
Deadline: Thursday, 4 September 2025, 7:00 PM IST
Objective
Automate and streamline the AV design and estimation process.
Check compliance of designs against AVIXA guidelines (room size, display size, table height, camera placement, ceiling lights, incidence angle, etc.).
Highlight guideline violations in red.
Fetch and attach technical specifications from OEM sources for each BOQ item.
Implement two workflows:
Technical approval
Commercial approval
Ensure cost/pricing fields are visible only to MD & CEO, Accounts, Purchase, Sales, and Finance.
Scope
1. Design & BOQ Automation
AI-assisted generation of designs and BOQs using playbooks, rules, and historical data.
Compare proposed designs with AVIXA-like recommendations.
2. Customer Experience
Web-based module for customers to enter requirements and view proposals.
Must include OTP authentication.
3. Support Chatbot (basic prototype)
Assist internal team/customers with queries and reference to past issues.
Data Flow Expectations
Input: Historical BOQs, design playbooks, AVIXA guidelines, customer questionnaires.
Output: BOQ with attached OEM spec sheets, compliance check report, and proposal workflow states.
Future capability: CAD drawing support (not in this demo).
Phased Rollout
Phase 1: BOQ generation and compliance check.
Phase 2: Workflow integration with Zoho CRM.
Phase 3: Chatbot and full AI-powered recommendations.
Deliverables
Draft BOQ with attached specs.
Compliance violations highlighted in red.
Role-based access for cost/pricing.
Demo of workflow approval sequence.
Customer portal view with OTP access.

## Avixa Standards
1. Display Standards (https://www.avixa.org/standards)
1. DISCAS (ANSI/AVIXA V201.01:2016 – Display Image Size for 2D Content)
Defines how to calculate image height / diagonal size based on viewing distance and task type (detailed vs basic viewing).
Provides formulas for minimum image size for legibility.
Also addresses viewing angles (horizontal and vertical).
2. Projected Image System Contrast Ratio (PISCR)
Defines required contrast ratio for content legibility in different environments.
Categories: Passive Viewing (7:1), Basic Decision Making (15:1), Analytical Decision Making (50:1), Full Motion Video (80:1).
2. Room Layout & Ergonomics
1. ANSI/AVIXA S202.01:2010 – Standard Guide for Audiovisual Systems Design & Coordination Processes
Addresses placement of displays, cameras, microphones, speakers, and furniture.
Specifies sightlines and field-of-view guidelines.
2. AVIXA F502.01 – AV Furniture Standard (in practice)
Defines table heights, seating layout, and ergonomics.
Seated eye height ≈ 1.2 m, used for camera placement reference.
3. Audio Standards
1. ANSI/ASA S12.60 – Acoustical Performance of Rooms
Recommended background noise levels (NC/RC < 35–40).
Reverberation time targets for classrooms/conference rooms.
2. Speech Intelligibility Standard (STI, per IEC 60268-16, adopted by AVIXA)
Defines clarity requirements (STI ≥ 0.6 for conferencing spaces).
4. Lighting Standards
AVIXA references IESNA (Illuminating Engineering Society) guidelines.
Key factors:
Incident light angle on display: typically 30°–60° to reduce glare.
Ambient lighting levels appropriate to content (video vs data).
5. Network & Control
AVIXA/InfoComm AV System Performance Verification (AV9000)
Provides guidelines for verifying AV system performance.
Covers signal paths, control, latency, reliability.
6. Documentation & Process
AVIXA S201.01 – Documentation Standard
Specifies minimum drawings/documents required for an AV project (signal flow diagrams, rack layouts, schematics).
AV9000 Quality Assurance Standard
Framework for testing, acceptance, and verification of AV systems.
Key Takeaways for Your Demo Project
Critical AVIXA rules to implement in your AI assignment:
1. DISCAS → display size vs viewing distance (mandatory).
2. Camera placement → lens height ≈ seated eye level (1.2 m ± tolerance).
3. Viewing angles → horizontal ≤ 60°, vertical ≤ 30°.
4. Lighting incidence → avoid direct glare (30°–60°).
5. Contrast ratio (PISCR) → enforce 15:1 or higher for conference.
6. Acoustics (background noise ≤ 40 dBA, STI ≥ 0.6).

## 3D Configurator
Some of the room confgurator examples
https://www.logitech.com/en-in/business/room-configurator.html#/configurator
https://support.yealink.com/en/room-configurator/index